## Slide 1: 2019 Statewide Medical & Health Exercise (SWMHE) in Ventura County
Final Planning Meeting

## Slide 2: Welcome
Housekeeping
  Cords for televisions
  Restrooms
Before the Exercise
Day of Exercise

## Slide 3: VCHCC Member Agreement Packet
All 3 components need to be complete by October 18th in order to receive Certificate of Participation.

## Slide 4: OPTIONAL Before the Exercise
Create Paper Patients
work with Controller & Evaluator to integrate patients into MSEL & EEG
Add Internal Objectives
work with Controller & Evaluator to integrate patients into MSEL & EEG
include in ExPlan

## Slide 5: Before the Exercise
Choose your Scenario
  3 different MSELs to chose from
Ensure that Players know how to submit a SitRep
Review ExPlan
Roles (Section 2 of exercise webpage)
Print (Section 7 of the exercise webpage)
  Exercise in Progress Signs  posted in exercise area at your site
  Sign-In Sheet  every participant at your site needs to sign in
  Player Handouts  provided to Players at sign-in
  Player Activity Logs (ICS 214), if applicable  provided to Players at sign-in or briefing

## Slide 6: Choosing Scenario Building Safety Evaluation Forms
All 3 forms are provided in C/E packet, but only need to pick one:
  No visible damage considerations may include future reports of unsafe conditions, repairs, or reinspection/further analysis.
  Partial damage considerations may include restricted use such as: no access to specific areas, brief entry to areas, etc.
  Significant damage considerations may include cascading events such as: partial collapse or damage to the building, utility failure, pollution/contamination (e.g. air quality or water), fire, explosion, chemical spill, etc.

## Slide 7
SCHEDULE

## Slide 8: Execution: day of the exercise
Sign-In
Facilitated at each site
ALL Players & Roles need to attend
Play
Two hours of Exercise Play
Will be announced via email on 10/17 as “StartEx” and “EndEx”
Follow MSEL (Controller) & fill out EEG (Evaluator)
Available for download under section 7 on the exercise webpage
Briefing (30 mins)
Provide to Players:
Player Handouts
ICS 214, if applicable
Submit SitReps via bit.ly/vcsitrep2019
Use Briefing PPT as guidance
Notes: PLAY
Only 2 emails we will send during play  everything else is provided in the Controller/Evaluator Packet as Inject Supplementals
Follow MSEL at the pace you need to  we are advising C/Es that they allow for more time for injects if need be and to move on to next inject if done early

## Slide 9
PARTICIPATING AGENCY | NUMBER/EMAIL
DOC | (805) 988-4089
Design Team Office | (805) 981-5301
Design Team Exercise lead | (805) 981-5331 (805) 981-5335 SWMHE@ventura.org
Questions During Exercise Play

## Slide 10: Situation Status Report (SitRep)
NEW link…will change January 1st of every year (given no current activation at that time)
Suggestions from July meeting are being vetted
Provide further input, post exercise (EEGs)
Copy of submitted SitRep is emailed to Report Creator
Bit.ly/vcsitrep2019

## Slide 11: Execution: wrap-up activities
Hot Wash (30 mins)
Facilitated at each site
Exercise Lead, Controller & Evaluator Debrief
Submit EEG
Email completed EEG
Use Hot Wash PPT as guidance
Assist Evaluator with EEG
Available for download under section 7 on the exercise webpage
to SWMHE@ventura.org
with the subject line “2019 EEG_[name of your site]”
by 5:00 pm on, Friday, October 18th.
Review player feedback forms, if applicable
Immediately following the “End Ex”, each site should:

## Slide 12: Tomorrow’s Controller & Evaluator Training
All Controllers & Evaluators will be provided detailed information regarding:
  MSEL
    Injects
    Building Safety Evacuation Forms
    Adding patients / internal objectives
  EEG
  Hot Wash
1:30 pm – 3:00 pm
2240 E Gonzales Rd. Suite 200
Oxnard, CA 93036

## Slide 13: After-Action Meeting
November 19th
9:30 am – 11:30 am
  Ventura County Behavioral Health Training Room
  1911 Williams Dr.
  Oxnard, CA 93036

## Slide 14: Thank you!
Questions may be directed to SWMHE@ventura.org